## Timeline and milestone
/ |  | Activities | Milestones | Q1 - 2025 | [12 empty] | Q2 - 2025 | [12 empty] | Q3- 2025 | [12 empty] | Q4 - 2025 | [12 empty] | Q1 - 2026 | [12 empty] | Q2 - 2026 | [12 empty] | Q3- 2026 | [12 empty] | Q4 - 2026 | [12 empty] | Q1 - 2027 | [12 empty] | Q2 - 2027
|  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  | SEPT |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  |  | Jun
|  |  |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 30 | 7 | 14 | 21 | 28
1 | Preparation | a. Study protocol design | 1. Internal protocol ethics discussion and development | bar: JAN 6 to MAR 17
2. Share and finalise protocol with Sight and Life team | bar: MAR 17 to MAR 24
3. Sending and process for ethical clearance to University of Mataram | bar: MAR 17 to MAR 24
4. Receive ethic approval | bar: APR 14 to APR 28
|  | b. Curriculum Building | 1. Modules and Topic list | bar: JAN 20 to FEB 10
2. Engage with MoH or Bapelkes | bar: JAN 20 to MAR 24; APR 14 to JUN 30
3. Modules and material making | bar: MAY 5 to DEC 29
4. Materials deployment to the LMS | bar: JAN 5 to MAR 30
|  | c. Approach, advocate and discuss with partners in districts and in national levels | 1. Engage with National, provincial, and ditrict level (Sounding of MMS project) | bar: JAN 13 to MAR 24; APR 14 to MAY 26
2. Secure support letters/MoUs from districts and related partners at provincial/national levels | bar: JAN 13 to MAR 24; APR 14 to MAY 26
3. Meet, discuss, and advocate with stakeholders for MMS system | bar: MAR 3 to MAR 24; APR 14 to MAY 26
|  | d. Population estimation | 1. Obtain Puskesmas (PHC) profile for number of yearly pregnant women and population | bar: FEB 3 to FEB 24
|  | e. Develop MMS System | 1. Create kobo form | bar: FEB 3 to MAR 24; APR 14 to JUN 30
2. Create Field Manual | bar: FEB 17 to MAR 24; APR 14 to JUN 30
|  | f. Recruit and train field worker | 1. Conduct open recruitment for CHP | bar: MAY 5 to MAY 19; JUN 16 to JUN 30
2. Field worker (CHP) training | bar: MAY 5 to MAY 19; JUN 16 to JUN 30; SEPT 1 to SEPT 29; FEB 2 to FEB 23; JUL 6 to JUL 27; DEC 7 to DEC 28
| MMS Kickoff | a. MMS Webinar | 1. Webinar preparation | bar: JAN 6 to MAR 24; APR 14 to APR 28
2. Campaign | bar: JAN 20 to MAR 24; APR 14 to APR 28
3. Host the webinar | bar: JUN 16
2 |  | b. MMS Blister and Kapsul preparation and Production | 1.Bidding Process | bar: APR 14 to APR 28
2. Design MMS packaging (Bottle, stips, and pill design) | bar: APR 14 to MAY 26
3. Determine batch release and expired date | bar: MAY 5 to MAY 26
4. Production MMS batch | bar: MAY 19 to JUN 23; SEPT 8 to SEPT 29; DEC 8 to DEC 29; MAR 9 to MAR 30; JUN 1 to JUN 22; SEPT 7 to SEPT 28; DEC 7 to DEC 28
5. Secure exemption, Halal Certification, and BPOM | bar: MAY 19 to SEPT 29
|  | c. MMS storage and distribution pipeline | 1. Secure agreement with Local Government for MMS storage, coordinator logistic | bar: MAY 19 to SEPT 29
2. Define SOP for storage and distriburion to pregnant women | bar: MAY 19 to SEPT 29
3 | Project Launch, Deployment and Upscaling | a. Conduct Demographic Survey | 1. Meeting with Head of Puskesmas for field deployment | bar: JUL 7 to AUG 11
2. Prepopulation to Polindes | bar: JUL 7 to SEPT 28
3. Prepoluation data monitoring | bar: AUG 4 to SEPT 28
|  | b. Coordinate Field Deployment | 1. Posyandu for Enrollment of Pregnant Woman | bar: AUG 4 to SEPT 28
2. Home Visit: Enrollment and Subsampling Baseline | bar: AUG 4 to SEPT 28
|  | c. Monitoring | 1. Giving and Monitoring MMS compliance | bar: AUG 4 to MAR 29
2. Sampling Midline | bar: NOV 3 to DEC 28
3. Sampling endline | bar: FEB 2 to MAR 29
| Project Performance & Control | a. Enhance data driven decision making | 1. Create reporting dashboards for daily data monitoring | bar: AUG 4 to MAR 30
2. Create manuals and processes for data-driven decisions via interpretation of dashboards for action | bar: AUG 4 to OCT 27
|  | b. Application and AI development | 1. Develop AI for MMS adherence monitoring | bar: MAY 5 to JUN 29
2. Application enhancement | bar: MAY 5 to JUN 29
|  | c. Monitor and evaluate the implementation of MMS project | 1. Create automated scripts to enable daily impact monitoring | bar: AUG 4 to OCT 27
4 |  |  | 2. Report quarterly summaries for coverage and quality of care, and the Head, Heart, Hand score for each FHW | bar: JAN 5 to JAN 26; JUL 6 to JUL 27; JAN 4 to JAN 25
5 | Report and Project Closing | a. Regular Reporting | 1. Regular quarter reporting/meeting to PHC | bar: JAN 5 to JAN 26; MAY 4 to MAY 25; SEPT 7 to SEPT 28; JAN 4 to JAN 25; MAY 3 to MAY 24
2. Half year report to Partner | bar: DEC 8 to DEC 29; JUN 1 to JUN 29; DEC 7 to DEC 28; Jun 7 to Jun 28
3. Half year report Meeting to DHO | bar: DEC 8 to DEC 29; JUN 1 to JUN 29; DEC 7 to DEC 28; Jun 7 to Jun 28
|  | b. Project Closing | 1. Announcement of project end to government | bar: APR 5 to APR 26
2. Disemination of project result | bar: Jun 7 to Jun 28
|  | c. Paper Writing | 1. Determinants analysis | bar: APR 5 to Jun 28
2. Paper Writing | bar: APR 5 to Jun 28
Eid Al-Fitr Holiday

## Jadwal MMS
2025-04-01
Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu
| 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30
Audiensi langsung ke Dikes KLU oleh Nurma, Arsika, Dinda
Bertemu staff pemerintahan Bupati KLU
Mei 2025
Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu
|  |  | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01
[10 empty] | Audiensi ke Bapeda oleh Bu Yuni dan Mas Tinus | Audiensi Wabup Lobar |  |  | Mas Toni kirim surat ulang ke Bupati Lotim dan Loteng |  | Final Draft Field Manual dan Question Bank KG | ODESS VISIT | Testing KG ke CHP |  |  | Mas Toni ke Dinkes NTB untuk sounding terkait logistik MMS, jika memang perlu nanti bisa buat diskusi bersama dengan tim lainnya
[10 empty] | Penandatangan MOU oleh Mas Tinus dan Mas Ariska | [5 empty] | ODESS VISIT |  |  | Kunjungan Wakil Bupati Loteng |  | MMS WORKSHOP
Permintaan Biodata Bidan KLU oleh Mas Arsika
Juni 2025
Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu
2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30
| Sounding MMS program serta logistik dinkes provinsi |  | Field Manual Versi 1 (Done) |  |  |  | Libur | KG Bidan KLU (PKM Bayan dan Senaru) | KG Bidan KLU (PKM Santong dan Kayangan) | KG Bidan KLU (PKM Gangga, Tanjung, RSUD KLU) | KG Bidan KLU (PKM Pemenang dan Nipah) |  |  | KG Bidan KLU (Klinik Hamzanwadi dan PKU Muhammadiyah) | KG MMS CHP Batch 2 | [7 empty] | Persiapan FGD
[9 empty] | Kobo refinement meeting | Survey Label MMS Meeting with HC | KG MMS CHP Batch 1 |  |  |  | Sebar undangan | Sebar undangan | Sebar undangan | Sebar undangan |  |  | Sebar undangan | Sebar undangan | Sebar undangan
Roadshow kesmas dan logistik dinkes
Juli 2025
Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu | Senin | Selasa | Rabu | Kamis | Jumat | Sabtu | Minggu
| 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31
| FGD LOBAR | FGD LOTIM | [5 empty] | Audiensi MMS di Kota Mataram | [7 empty] | Audiensi Provinsi NTB Online | [7 empty] | Audiensi MMS di Lotim |  |  |  | Deadline Transkripsi FGD
Jadwalkan pengantaran surat permintaan tanggal posyandu, Lobar, KLU, dan Mataram
Nurma mengurus inportasi
International registartion
Protokol Kualitatif